## Template
Projet topic:
Team membes:
Iteration 1 - presentation 20.4 | A |  |  | B | C
Date - End of | Task | Time estimation | Actual time
Iteration 2
Week 1
Week 2
Week 3
Week 4
Iteration 2 - presenatation 18.5
Iteration 3
Week 1
Week 2
Week 3
Week 4
Iteration 3 - presenatation 22.6
Final presentation

## Team 7
Projet topic: Literature review analysis regarding gender gaps between women and men in the high-tech industry
Team membes:
Iteration 1 - presentation 20.4 | Yuval Shem Tov |  |  | Yael Bellaiche
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Iteration 2
Week 1 - 27.04 | 1) Literature review 2) Find relavant datasets | 3h 2h |  | 1) Literature review 2) Find relavant datasets | 3h 2h
Week 2 - 04.05 | 1) Think what should be relavant data 2) Think how to filter the relavant data | 4h 1h |  | 1) Think what should be relavant data 2) Think how to filter the relavant data | 4h 1h
Week 3 - 11.05 | 1) Summarize all the relevant questions 2) Start studying relevant data analysis methods | 4h 1h |  | 1) Summarize all the relevant questions 2) Start studying relevant data analysis methods | 4h 1h
Week 4 - 18.05 | 1) Continue studying relevant data analysis methods 2) Start implementation 3) Write the iteration 2 presentation | 3h 1h 1h |  | 1) Continue studying relevant data analysis methods 2) Start implementation 3) Write the iteration 2 presentation | 3h 1h 1h
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 - 01.06 | 1) Analyze the data that was collected | 5h |  | 1) Analyze the data that was collected | 5h
Week 2 - 08.06 | 1) Use the data collected to answer the research questions | 5h |  | 1) Use the data collected to answer the research questions | 5h
Week 3 - 15.06 | 1) Learn relevant statistic tools to summarize results 2) Start analyzing results using the tools learned above | 4h 1h |  | 1) Learn relevant statistic tools to summarize results 2) Start analyzing results using the tools learned above | 4h 1h
Week 4 - 22.06 | 1) Finishwith the data analysis 2) Write final presentation | 3h 2h |  | 1) Finishwith the data analysis 2) Write final presentation | 3h 2h
Iteration 3 - presenatation 22.6
Final presentation - 29.06

## Team 8
Projet topic: Finding ethnic & gender biasses by researching interview transcripts
Team membes:
Iteration 1 - presentation 20.4 | Etay Kofman |  |  | Amit Miara |  |  | Itai palti
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Iteration 2
Week 1 - 27.04 | Literature Review | 5h |  | Literature Review | 5h |  | Literature Review | 5h
Week 2 - 04.05 | Learn about speech-to-text algorithms | 5h |  | Learn about speech-to-text algorithms | 5h |  | Learn about speech-to-text algorithms | 5h
Week 3 - 11.05 | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 2h 3h |  | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 2h 3h |  | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 2h 3h
Week 4 - 18.05 | Learn NLP algorithms for extracting data from text. Choosing NLP technique/models. | 3h 2h |  | Learn NLP algorithms for extracting data from text. Choosing NLP technique/models. | 3h 2h |  | Learn NLP algorithms for extracting data from text. Choosing NLP technique/models. | 3h 2h
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 - 01.06 | Start implmenting models and training. | 5h |  | Start implmenting models and training. | 5h |  | Start implmenting models and training. | 5h
Week 2 - 08.06 | Analyze data | 5h |  | Analyze data | 5h |  | Analyze data | 5h
Week 3 - 15.06 | Fixes and more iteraions. | 5h |  | Fixes and more iteraions. | 5h |  | Fixes and more iteraions. | 5h
Week 4 - 22.06 | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h 1h |  | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h 1h |  | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h 1h
Iteration 3 - presenatation 22.6
Final presentation - 29.06

## Team 2
Projet topic: Find most compatible applicants based on job description and CVs
Team membes:
Iteration 1 - presentation 20.4 | Dor Golfaiz |  |  | Itamar Shichrur |  |  | Yahav Sasson
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Iteration 2
Week 1 - 27.04 | Literature Review | 6h |  | Literature Review | 6h |  | Literature Review | 6h
Week 2 - 04.05 | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 5h |  | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 5h |  | Gathering data from company HR from each of our companies. Funneling relevant interviews. | 5h
Week 3 - 11.05 | Learn about OCR (Optical character recognition) | 4h |  | Learn about NLP (Natural language processing), and think how it can be applied to our needs | 4h |  | Learn about current AI tools out in the market, regarding resume screening | 4h
Week 4 - 18.05 | Start implementing OCR on scanned resumes, and test success rates compared to the human eye. | 5h |  | Find job description datasets, with as much data attached to it as possible | 5h |  | Find CV datasets, with as much data attached to it as possible | 5h
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 - 01.06 | Start implementing OCR models and try predicting an applicants compatability | 5h |  | Start implementing OCR models and try predicting an applicants compatability | 5h |  | Start implementing OCR models and try predicting an applicants compatability | 5h
Week 2 - 08.06 | Test the results and analyze the data based on data collected in self's company | 4h |  | Test the results and analyze the data based on data collected in self's company | 4h |  | Test the results and analyze the data based on data collected in self's company | 4h
Week 3 - 15.06 | Repeat iterations over prediction tools to get better results, and repeat stages of week 1 and 2 | 7h |  | Repeat iterations over prediction tools to get better results, and repeat stages of week 1 and 2 | 7h |  | Repeat iterations over prediction tools to get better results, and repeat stages of week 1 and 2 | 7h
Week 4 - 22.06 | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h |  | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h |  | Deducting conclusions, and answering our research question. Final presentation preperation. | 4h
Iteration 3 - presenatation 22.6
Final presentation - 29.06

## Team 1
Projet topic: | the connection between student positions and academic/professional success
Team membes:
| A - noa barak |  |  | B - guy girmonsky |  |  | C - lior ladin
Iteration 1 | Task | Time estimation | Actual time | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Week 1 | Finding out what similar topics have been researched before - literature | 5h | 4h | Research ways to gather the data | 5h | 4h | Speaking with people form hr filed - ask about our topic and DB | 5h | 6h
Week 2 | Conduct literature review on student positions and productivity measures | 8h | 8h | Create a presentation for class | 2h | 3h | Determining what kind of data should be gathered | 3h | 4h
Iteration 1 - presenatation 20.4
Iteration 2
Week 1 | Creating surveys for ungraduates and graduates | 6h |  | Creating surveys for ungraduates and graduates | 6h |  | Creating surveys for ungraduates and graduates | 6h
Week 2 | Reconduct literature review on the updated subject | 6h |  | Manual scraping from LinkedIn for approriate survery candidates | 7h |  | Reching out to students around campus with the survey | 7h
Week 3 | Cleaning data | 5h |  | Cleaning data | 4h |  | Cleaning data | 4h
Week 4 | Create presentation 2 | 3h |  | Learning models for prediction | 5h |  | Learning models for prediction | 5h
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 | Statistical Analysis of the data | 5h |  | Implement models for training | 5h |  | Visualization of the data | 5h
Week 2 | Statistical Analysis of the data | 5h |  | Implement models for training | 5h |  | Visualization of the data | 5h
Week 3 | Buffer week for fixing issues etc | 5h |  | Buffer week for fixing issues etc | 5h |  | Buffer week for fixing issues etc | 5h
Week 4 | Prepare the third presentation | 3h |  | Deducting conclusions, and answering our research question. | 3h |  | Deducting conclusions, and answering our research question. | 3h
Iteration 3 - presenatation 22.6 | Prepare final presentation |  |  | Prepare final presentation |  |  | Prepare final presentation
Final presentation

## Team 3
Projet topic:
| Team membes: | [8 empty] | Meta-Tasks:
Iteration 1 - presentation 20.4 | A - Noy Cohen |  |  | B- Inbal Marom |  |  | C - Itamar Israelit |  |  | tasks
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time | Task | Time estimation | Actual time | extract top 20 tech-companies
Iteration 2 | [9 empty] | extract data linkedin | scraping linkedin
Week 1 | create DB | 1 |  | review API - extract data facebook | 5 |  | review API - extract data linkedin | 1 |  | extract data instagram | API instagram
| scraping - extract data linkedin | 9 |  |  |  |  | extract and insert DB top 20 tech-companies (company name, company size, budget, url to linkedin, facebook, intagram) | 4 |  | surveys
Week 2 |  |  |  | review API - extract data instagram | 5 |  | review API - extract data twiter | 7 |  | extract data facebook | scraping facebook
Week 3 | db scheme linkedin | 1 |  | db scheme facebook+ instagram | 2 |  | db scheme twiter | 1 |  | create db | nova user
| insert data from linkedin to DB | 3 |  | insert data from facebook to DB | 2 |  | insert data from twiter to DB | 2
Week 4 | surveys - create surveys | 2 |  | insert data from instagram to DB | 2 |  | surveys - surveys distribution, insert to DB | 2 |  | preparing data | db scheme | transform and log data
| create presentation and get to know data | 3 |  | create presentation and get to know data | 3 |  | create presentation and get to know data | 3
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 | planing machine learning model | 3 |  | planing machine learning model | 3 |  | planing machine learning model | 3
Week 2 | [9 empty] | data | companies activity | likes
Week 3 | [10 empty] | people engagement | students surveys
Week 4 | [11 empty] | applications linkedin
Iteration 3 - presenatation 22.6 | [11 empty] | posts shares and likes
Final presentation

## team 4
Projet topic:
determining which jobs require BCS | Team members: Amichai Skaliter |  |  | Team members: Shelly Sela
| Task | Time estimation | Actual time | Task | Time estimation | Actual time
| Finding out what similar topics have been researched before | 5 | 7 | Determining what kind of data should be gathered | 9 | 14
| Articulating and pinpointing the research problem | 4 | 6 | Speaking with people from different work fields and university programs to check whether our topic is interesting/relevant | 8 | 9
| Discuss our topic with experienced colleagues to gather their insights | 6 | 6 | Research ways to gather the data | 8 | 12
| Rephrasing and polishing our main topics | 4 | 4 | Pros and cons for each data gathering option | 6 | 7
| Create a presentation for class | 6 | 8 | Refine the presentation | 2 | 5
| Buffer for discussions and decision making | 3 | 3 | Buffer for discussions and decision making | 3 | 3
| Learn how to do a scraping script from Glassdoor | 9 | 20 | Learn how to do a scraping script from LinkedIn | 9 | 18
| Plan together the next iteration + time allocation | 3 | 3 | Plan together the next iteration + time allocation | 3 | 3
Iteration 1 - presentation 20.4
Iteration 2 | understand after the presenatation which parts are most appealing | 2 |  | in-depth work with the collected data (cleaning it) | 12
Week 1 | refining the presentation | 4 |  | verifying the data collected is the most relevant to our topic | 2
Week 2 | thinking togethor which model to choose for working with our data | 6 |  | thinking togethor which model to choose for working with our data | 6
Week 3 | getting to know data science modules for python | 2 |  | learning which data science modules can help with our project | 4
Week 4 | analyzing our data, Planning the next iteration | 11 |  | analyzing our data, Planning the next iteration | 11
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 | re-thinking our model to make sure it's the best fit for our project | 3 |  | refining our presentation | 3
Week 2 | showing our project to co-workers to gather opinions and suggestions | 3 |  | figure out what we "missed out" and should add | 4
Week 3
Week 4
Iteration 3 - presenatation 22.6
Final presentation

## Team 5
Project topic: | Gender bias in job descriptions
Team members:
Iteration 1 - presentation 20.4 | Liron Cohen |  |  | Ofer Tlusty |  |  | Yuval Mor
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Iteration 2
Week 1 - 27.04 | 1) Familiarize with the research plan and data collection tools 2) Conduct literature review on gender-exclusive language in job descriptions 3) Extract job descriptions from LinkedIn with the labor study team | 2 hours 2 hours 1 hour |  | 1) Familiarize with the research plan and data collection tools 2) Conduct literature review on gender-exclusive language in job descriptions | 2 hours 3 hours |  | 1) Familiarize with the research plan and data collection tools 2) Conduct literature review on gender-exclusive language in job descriptions | 2 hours 3 hours
Week 2 - 04.05 | 1) Initial statistical analysis of the aforementioned job descriptions 2) Extract a report of the results for labor study's survey | 4 hours 1 hour |  | 1) Initial statistical analysis of the aforementioned job descriptions 2) Extract a report of the results for labor study's survey | 4 hours 1 hour |  | 1) Initial statistical analysis of the aforementioned job descriptions 2) Extract a report of the results for labor study's survey | 4 hours 1 hour
Week 3 - 11.05 | 1) Find relevant datasets from Kaggle & Ocean 2) Start cleaning the found data | 2 hours 3 hours |  | 1) Create list of selected job descriptions for expert opinion 2) Find existing scoring methods to be used as expert opinion | 3 hours 2 hour |  | 1) Find relevant datasets from other websites 2) Start cleaning the found data | 2 hours 3 hours
Week 4 - 18.05 | 1) Continue cleaning the data 2) Creating the presentation 3) Iteration retrospect | 2 hours 2 hours 1 hour |  | 1) Continue cleaning the data 2) Creating the presentation 3) Iteration retrospect | 2 hours 2 hours 1 hour |  | 1) Continue cleaning the data 2) Creating the presentation 3) Iteration retrospect | 2 hours 2 hours 1 hour
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 - 01.06 | 1) Finish cleaning and organizing the data | 5 hours |  | 1) Finish cleaning and organizing the data | 5 hours |  | 1) Finish cleaning and organizing the data | 5 hours
Week 2 - 08.06 | 1) Analysis of the results from the labor study's survey with the team 2) Work on integration of the results into our analysis | 3 hours 2 hours |  | 1) Analysis of the results by the scoring method chosen to be used as expert opinion 2) Work on integration of the results into our analysis | 3 hours 2 hours |  | 1) Start creating an improved statistical analysis that can extend our gender-exclusive terms list | 5 hours
Week 3 - 15.06 | 1) Help finish creating an improved statistical analysis that can extend our gender-exclusive terms list | 5 hours |  | 1) Help finish creating an improved statistical analysis that can extend our gender-exclusive terms list | 5 hours |  | 1) Finish creating an improved statistical analysis that can extend our gender-exclusive terms list | 5 hours
Week 4 - 22.06 | 1) Organizing the results and documentation of the project 2) Creating the presentation | 4 hours 1 hour |  | 1) Organizing the results and documentation of the project 2) Creating the presentation | 4 hours 1 hour |  | 1) Organizing the results and documentation of the project 2) Creating the presentation | 4 hours 1 hour
Iteration 3 - presenatation 22.6 | 1) Finish the final presentation 2) project retrospect | 4 hours 1 hour |  | 1) Finish the final presentation 2) project retrospect | 4 hours 1 hour |  | 1) Finish the final presentation 2) project retrospect | 4 hours 1 hour
Final presentation - 29.06

## Team 6
Projet topic: Is the Bachelor's degree GPA a good predicate for Master's degree success?
Team membes:
Iteration 1 - presentation 20.4 | Ron |  |  | Shaked
Date - End of | Task | Time estimation | Actual time | Task | Time estimation | Actual time
Iteration 2
Week 1 - 27.04 | 1) Literature review 2) Dataset search (Kaggle) | 3h 2h |  | 1) Literature review 2) Dataset search (Kaggle) | 3h 2h
Week 2 - 04.05 | 1) Formulate the "success" factor 2) Start thinking about the needed data | 4h 1h |  | 1) Formulate the "success" factor 2) Start thinking about the needed data | 4h 1h
Week 3 - 11.05 | 1) Finish deciding what is the rquired data 2) Start building the questionaries | 4h 1h |  | 1) Finish deciding what is the rquired data 2) Start building the questionaries | 4h 1h
Week 4 - 18.05 | 1) Finish building the questionaries 2) Start sending out the qustionaries 3) Write the iteration 2 presentation | 3h 1h 1h |  | 1) Finish building the questionaries 2) Start sending out the qustionaries 3) Write the iteration 2 presentation | 3h 1h 1h
Iteration 2 - presenatation 18.5
Iteration 3
Week 1 - 01.06 | 1) Start analysing the data | 5h |  | 1) Start analysing the data | 5h
Week 2 - 08.06 | 1) Continue data anaysis 2) Start building the model | 3h 2h |  | 1) Continue data anaysis 2) Start building the model | 3h 2h
Week 3 - 15.06 | 1) Finish building the model 2) Start to analyize the results | 4h 1h |  | 1) Finish building the model 2) Start to analyize the results | 4h 1h
Week 4 - 22.06 | 1) Finish the result analysis 2) Writing the final project representation | 3h 2h |  | 1) Finish the result analysis 2) Writing the final project representation | 3h 2h
Iteration 3 - presenatation 22.6
Final presentation - 29.06